## Part 1: Software Requirements Specification (SRS)

## Purpose and Scope

Purpose

The main purpose of this project is to develop a Produce Intake and Payment Management System for the Whagi Valley Produce Cooperative. The cooperative currently records the produce deliveries using a traditional paper-based processes while also managing member payments manually. This approach creates difficulties in recording, storing, retrieving and maintaining records, tracking, and generating reports.

This proposed project will improve efficiency, accuracy, ensuring accountability, and reporting while also supporting the operation in its rural environment with its imited internet connectivity.

Scope

The system will:

- Register and maintain cooperative member records

- Record produce deliveries received at the depot

- Calculate the payments based on the crop type, quantity, and approving the price

- Generate delivery acknowledgements

- Track payments status and history

- Generate management and financial reports

- Operate when internet access is available

- Synchronize records with the main office when connectivity become available again.

The system shall not:

- Process online banking transactions

- Manage transportation services

- Manage external buyer relationships

- Support advanced analytics in the first release

## Business Context and Stakeholders

  - Business Context

The Whagi valley cooperative purchases produce from local farmers and coordinates the sale of agricultural products, where it has approximately 300 members who supply produce through a rural depot. The cooperative currently relies on traditional manual record keeping through paper forms and books. This process creates delays in processing records, and processing member payments, difficulties in tracking deliveries, and challenges in generating an accurate report.

The depot experiences unreliable internet access and usually operates on solar power and backup generators. Thus, the system must be able to support offline operation and data synchronization when the connectivity becomes available again.

  - Stakeholders

- Cooperative Manager

Responsibilities:

- Monitor cooperative performance

- Review reports

- Approve pricing structure

- Resolve disputes

System Needs:

- Access to management reports

- Ability to lock daily price sheets

- Visibility of payment activities

- Depot Clerk

Responsibilities:

- Record produce deliveries

- Maintain member records

- Generate delivery acknowledgements

- Track payment status

System Needs:

- A simple and easy to use interface

- Fast data entry

- Offline capability

- Cooperative Committee

Responsibilities:

- Oversee the operations

- Approve deductions and policies

- Monitor financial performance

System Needs:

- Access to summary reports

- Review of payment information

- Farmers (Cooperative members)

Responsibilities:

- Deliver produce

- Receive payments

System Needs:

- Accurate transaction records

- Fair and transparent payment calculations

- Reduced payment disputes

## Functional Requirements

FR-1: The system shall record produce intake including member number, crop, grade, kilograms, date, and price.

FR-2: The system shall operate fully offline at the depot.

FR-3: The system shall prevent depot clerks from changing locked price.

FR-4: The system shall generate a printable acknowledgement for each produce delivery.

FR-5: The system shall allow the manager to create a lock daily price sheets by crop and grade.

## Non-Functional Requirements

NFR-1: The system shall function without internet connectivity.

NFR-2: The system shall provide simple data entry suitable for depot staff with limited technical training.

NFR-3: The system shall support recovery after power interruption.

NFR-4: The system shall process normal transactions within three seconds.

NFR-5: The system shall preserve data during unexpected shutdown and power interruptions.

NFR-6: The system shall remain operational during normal depot business hours.

NFR-7: The system shall provide a simple interface suitable for staff with limited technical experience.

NFR-8: The system shall use a layered architecture to support future maintenance and upgrades.

NFR-9: The system shall prevent duplicate records during synchronization.

## Constraints and Business Rules

Constraints

- Power Constraints

The system must operate within the limitation of the rural environment of Papua New Guinea, and the depot relies on solar power and backup generators. The system must automatically save data and recover safely after power interruptions.

- Device Constraints

The system must operate on standard laptop computers without requiring any specialized hardware.

- Approval Structure Constraints

The changes to prices, it’s deductions, and the payment policies all require approval from authorized management. These access controls must enforce the approval requirements for security purposes.

Business Rules

- BR-1: Each cooperative member must have a unique member ID.

- BR-2: Changes to deductions or payment policy require member committee approval.

- BR-3: Once a day’s price sheet is locked, the depot clerk cannot modify prices.

- BR-4: Every produce delivery must be linked to the registered member.

- BR-5: only managers can create or modify daily prices

- BR-6: Only authorized personnel may approve payment-related changes.

- BR-7: Transactions from history shall not be permanently deleted.

## Glossary

| Term | Definition |
| --- | --- |
| Member | A registered farmer supplying produce to the cooperative. |
| Depot Clerk | A staff member responsible for daily transaction and processing. |
| Payment Status | Indicates whether payment is completed or pending. |
| Produce Intake | The recording of produce delivered by a member. |
| Price Sheet | The approved produce prices used for payment calculation. |
| Synchronization | Transfer locally stored records to the central database. |
| Transaction | A produce delivery and its associated payment record. |
| report | A summary or all operational or financial information. |

## Part 2: Estimate and Work Schedule

- Estimation Assumptions and Method

  - Assumptions

The following assumptions were made:

- One developer will complete the project.

- Existing depot laptops will be used.

- Cooperative staff will be available for consultation.

- Functional and user acceptance testing will be performed.

- The first release will focus on core business functionality.

- Minimal training will be required due to the simple user interface.

  - Estimation Method

The bottom-up estimation method was used. The project was divided into smaller tasks, and each of these tasks was estimated independently from each of the increments. The individual estimates were then combined to produce a total estimate project effort.

This method helps prove accuracy because all the task were considered separately before calculating the overall duration and range of the project.

## Task Breakdown Structure

## Time Estimates, Assumptions and Reasoning

- Increment 1: Project Setup and Member Registration

| Task | 0 | M | P | E |
| --- | --- | --- | --- | --- |
| Project setup | 1 | 2 | 4 | 2.17 |
| Database schema | 2 | 4 | 8 | 4.33 |
| Member registration | 4 | 6 | 10 | 6.33 |
| Member search | 2 | 4 | 8 | 4.33 |
| Member update function | 2 | 4 | 8 | 4.33 |
| Testing | 2 | 4 | 8 | 4.33 |
| Total Increment 1 = 25.82 Hours |  |  |  |  |

- Increment 2: produce Intake Recording

| Task | 0 | M | P | E |
| --- | --- | --- | --- | --- |
| Intake from design | 2 | 4 | 8 | 4.33 |
| Produce capture function | 4 | 6 | 10 | 6.33 |
| Grade validation | 2 | 4 | 8 | 4.33 |
| Storage of intake records | 2 | 4 | 8 | 4.33 |
| Testing | 2 | 4 | 8 | 4.33 |
| Total Increment 2 = 23.65 hours |  |  |  |  |

- Increment 3: Payment Calculation

| Task | 0 | M | P | E |
| --- | --- | --- | --- | --- |
| Price sheet | 2 | 2 | 8 | 4.33 |
| Payment calculation | 4 | 6 | 12 | 6.67 |
| Validation of calculations | 2 | 4 | 8 | 4.33 |
| User interface updates | 2 | 4 | 8 | 4.33 |
| Testing | 2 | 4 | 8 | 4.33 |
| Total Increment 3 = 24.00 hours |  |  |  |  |

- Increment 4: Delivery Acknowledgements

| Task | 0 | M | P | E |
| --- | --- | --- | --- | --- |
| Receipt template design | 2 | 4 | 8 | 4.33 |
| Generate acknowledgement feature | 4 | 6 | 10 | 6.33 |
| Print formatting | 2 | 4 | 8 | 4.33 |
| Data validation | 2 | 4 | 8 | 4.33 |
| Testing | 2 | 4 | 8 | 4.33 |
| Total Increment 4 = 23.65 hours |  |  |  |  |

- Increment 5: Payment Tracking

| Task | 0 | M | P | E |
| --- | --- | --- | --- | --- |
| Payment status module | 3 | 5 | 10 | 5.50 |
| Outstanding payments list | 2 | 4 | 8 | 4.33 |
| Payment history records | 2 | 4 | 8 | 4.33 |
| Search functionality | 2 | 4 | 8 | 4.33 |
| Testing | 2 | 4 | 8 | 4.33 |
| Total Increment 5 = 22.82 hours |  |  |  |  |

- Increment 6: Reporting

| Task | 0 | M | P | E |
| --- | --- | --- | --- | --- |
| Produce reports | 3 | 5 | 10 | 5.50 |
| Payment reports | 3 | 5 | 10 | 5.50 |
| Outstanding payment reports | 2 | 4 | 8 | 4.33 |
| Report filtering | 2 | 4 | 8 | 4.33 |
| Testing | 2 | 4 | 8 | 4.33 |
| Total Increment 6 = 24.00 hours |  |  |  |  |

- Increment 7: Synchronization

| Task | 0 | M | P | E |
| --- | --- | --- | --- | --- |
| Local queue design | 3 | 5 | 10 | 5.50 |
| Synchronization logic | 4 | 8 | 16 | 8.67 |
| Duplicate checking | 2 | 4 | 8 | 4.33 |
| Connectivity testing | 2 | 4 | 10 | 4.67 |
| Testing | 2 | 4 | 8 | 4.33 |
| Total Increment 7 = 27.50 hours |  |  |  |  |

- Increment 8: Security, Deployment, and Documentation.

| Task | 0 | M | P | E |
| --- | --- | --- | --- | --- |
| User authentication | 3 | 5 | 10 | 5.50 |
| Role management | 2 | 4 | 8 | 4.33 |
| User documentation | 2 | 4 | 8 | 4.33 |
| Deployment preparation | 2 | 4 | 8 | 4.33 |
| Final Testing | 3 | 5 | 10 | 5.50 |
| Total Increment 8 = 24.00 hours |  |  |  |  |

- Total Project Effort = 194.44 Hours

Estimate Project Duration

We assume approximately 15 productive hours per week;

195.44 ÷15 = 10.03 weeks.

Therefore, the project would be expected to take approximately 13 weeks, which aligns with the eights increment delivery schedule and also allows for enough time for testing, the stakeholders feedback, and then the deployment. Thus, we would say is a more realistic estimate than the 96-hour estimate when we take into consideration the changes that can happen in a person’s week, as it accounts for the planning, its development time, the testing period, reviewing the project, and deploying the project.

## Work Schedule

| Week | Increment | Deliverable |
| --- | --- | --- |
| Week 1-2 | 1 | Project setup, database creation, member registration and management |
| Week 3-4 | 2 | Produce intake recording and storage |
| Week 5 | 3 | Payment calculation and price sheet management |
| Week 6 | 4 | Delivery acknowledgement generation |
| Week 7-8 | 5 | Payment tracking and payment management |
| Week 9-10 | 6 | Produce reports, payment reports, and reporting features |
| Week 11 | 7 | Synchronization functionality and connectivity testing |
| Week 12-15 | 8 | Security features, system testing, documentation . |

Risks Affecting the Schedule

- Unreliable internet connectivity

- Power interruptions (especially at nights)

- Limited availability of stakeholders

- Requirements changes during developments

## Dependency Triangle Analysis

- Hold Scope

This focuses on delivering all eight planned increments and maintaining the scope of the full project. This approach makes sure that all the stakeholders’ requirements are addressed and met, including the management, produce intake recording, payment tracking, reporting, and synchronization and the security features.

Holding the scope would be recommended because the cooperative’s main issues faced are record keeping payment management, reporting, and the unreliable internet connectivity. Thus, delivering all eight increments ensures that the final project delivered is not delivered partly but as a complete solution.

AI Declaration

Microsoft copilot was used to assist with brainstorming and especially used to understand lecture notes to calculate the estimate section. It was also used to check against the criteria and edit the final content.

## Reference

CMN224 Week 6 Lecture: Estimation and Work Schedules.